## Task List
Job # | Task # | Stage | Super | Code | FinList# | Ref | KT | KTsort | Task | Supplier/Trade | WhosTask | N/A | Ordered | Completed | PO # | PORefNum | PreReq | Offset | SqftDay | MoneyDay | MoneyCode | TaskLen | ODate | Prjd Start | Calc Start | Prjd Finish | Calc Finish | Actual Finish | Memo | Prog
1 | 10 | A |  |  |  |  | FALSE |  | Open up Files | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 20 | A |  |  |  |  | FALSE |  | Congratulations letter completed | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 30 | A |  |  |  |  | FALSE |  | Letter to Tom Spratlin | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 40 | A |  |  |  |  | FALSE |  | Contract Signed | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 70 | A |  |  |  |  | FALSE |  | Deposit Received | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 80 | A |  |  |  |  | FALSE |  | Customer info sheet completed | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 130 | A |  |  |  |  | FALSE |  | Blueprints & specs approved @ sign-off | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 140 | A |  |  |  |  | FALSE |  | Make all changes from sign off & change order | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 150 | A |  |  |  |  | FALSE |  | Received final plot plan from surveyor | Aubrey Funk | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 160 | A |  |  |  |  | FALSE |  | Engineer stamp for cultured stone | Aubrey Funk | Tara Peters | FALSE | FALSE | FALSE
1 | 170 | A |  |  |  |  | FALSE |  | Engineer stamp for structural details | Aubrey Funk | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 180 | A |  |  |  |  | FALSE |  | Apply for architectrual app./approval | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 200 | A |  |  |  |  | FALSE |  | Building Permit | Strathcona County | Tara Peters | FALSE | FALSE | FALSE
1 | 210 | A |  | 1320 |  |  | FALSE |  | Gas application | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 220 | A |  |  |  |  | FALSE |  | Complete estimate done | Aubrey Funk | Aubrey Funk | FALSE | FALSE | FALSE
1 | 225 | A |  |  |  |  | FALSE |  | Estimate entered into Peachtree | Tara Peters | Rob Salvalaggio | FALSE | FALSE | FALSE
1 | 240 | A |  |  |  |  | FALSE |  | Plans (Customer sign off)-2 | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 250 | A |  |  |  |  | FALSE |  | Plans (Financing appraisal)-1 | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 260 | A |  |  |  |  | FALSE |  | Plans (Building Permits)-2 | Aubrey Funk | Aubrey Funk | FALSE | FALSE | FALSE
1 | 270 | A |  |  |  |  | FALSE |  | Plans (Engineer)-1 | Aubrey Funk | Aubrey Funk | FALSE | FALSE | FALSE
1 | 280 | A |  |  |  |  | FALSE |  | Plans (Surveryor)-1 | Aubrey Funk | Aubrey Funk | FALSE | FALSE | FALSE
1 | 290 | A |  |  |  |  | FALSE |  | Plans (Architectural approval)-1 | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 300 | A |  |  |  |  | FALSE |  | Plans (Sales staff)-1-3 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 310 | A |  |  |  |  | FALSE |  | Plans (Windows)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 320 | A |  |  |  |  | FALSE |  | Plans (Roof/Floor Trusses)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 330 | A |  |  |  |  | FALSE |  | Plans (Plumbing)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 340 | A |  |  |  |  | FALSE |  | Plans (Heating)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 350 | A |  |  |  |  | FALSE |  | Plans (Electrical)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 355 | A |  |  |  |  | FALSE |  | Plans (Lighting)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 370 | A |  |  |  |  | FALSE |  | Plans (Cribber)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 372 | A |  |  |  |  | FALSE |  | Plans (ICF Manufacturer)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 375 | A |  |  |  |  | FALSE |  | Plans (Grade Beam Cribber)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 380 | A |  |  |  |  | FALSE |  | Plans (Joisting)-1 | Tara Peters | Tara Peters | TRUE | FALSE | FALSE
1 | 390 | A |  |  |  |  | FALSE |  | Plans (Framer)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 395 | A |  |  |  |  | FALSE |  | Plans (Flat Work)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 400 | A |  |  |  |  | FALSE |  | Plans (Site Super)-1 | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 410 | A | 3 |  |  |  | FALSE |  | Customer Choice Meeting Arranged | Tara Peters | Tara Peters | FALSE | FALSE | FALSE
1 | 420 | B |  |  |  |  | FALSE |  | Signs PO | Tara Peters | Tara Peters | FALSE | FALSE | FALSE |  | 730
1 | 440 | B |  |  |  |  | FALSE |  | Sewer, storm and water PO | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 560
1 | 441 | B |  |  |  |  | FALSE |  | Excavation, loading and hauling PO | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 571
1 | 442 | B |  |  |  |  | FALSE |  | Backfill house PO | Excat Excavating Inc. |  | FALSE | FALSE | FALSE |  | 572
1 | 443 | B |  |  |  |  | FALSE |  | Backfill Grade Beam / Cut Detached Garage | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 573
1 | 444 | B |  |  |  |  | FALSE |  | Pre-Grade PO | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 574
1 | 445 | B |  |  |  |  | FALSE |  | Final Rough-Grade PO | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 576
1 | 450 | B |  |  |  |  | FALSE |  | Gas line PO | Atco Gas |  | FALSE | FALSE | FALSE |  | 80
1 | 460 | B |  |  |  |  | FALSE |  | Concrete-Footings PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 820
1 | 470 | B |  |  |  |  | FALSE |  | Concrete-Walls PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 810
1 | 480 | B |  |  |  |  | FALSE |  | Concrete Pumping PO | A&B Concrete Pumping |  | FALSE | FALSE | FALSE |  | 10
1 | 490 | B |  | 2230 |  | 259 | FALSE |  | Floor truss PO | Igloo Building Supplies | Aubrey Funk | FALSE | FALSE | FALSE |  | 350
1 | 500 | B |  |  |  |  | FALSE |  | Cribbing first package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 370
1 | 510 | B |  | 1620 |  |  | FALSE |  | Cribber PO | Fearon Construction | Bruno Salvalaggio | FALSE | FALSE | FALSE |  | 280
1 | 520 | B |  |  |  |  | FALSE |  | Sump pit PO | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 535
1 | 530 | B |  |  |  |  | FALSE |  | Weeping tile, dampproofing and gravel PO | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 530
1 | 535 | B |  |  |  |  | FALSE |  | Basement gravel PO | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 536
1 | 540 | B |  | 2230 |  |  | FALSE |  | Roof Truss PO | Igloo Building Supplies | Aubrey Funk | FALSE | FALSE | FALSE |  | 360
1 | 550 | B |  |  |  | 13055 | FALSE |  | Garage roof truss PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 365
1 | 560 | B |  |  |  |  | FALSE |  | Cribbing second package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 380
1 | 570 | B |  |  |  |  | FALSE |  | Joist Labour PO | David Mills | Bruno Salvalaggio | FALSE | FALSE | FALSE |  | 210
1 | 580 | B |  |  |  |  | FALSE |  | Piles drilling PO | Waytec Enterprises |  | FALSE | FALSE | FALSE |  | 710
1 | 590 | B |  |  |  |  | FALSE |  | Concrete-Piles PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 800
1 | 595 | B |  |  |  |  | FALSE |  | Grade Beam Cribbing Package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 390
1 | 600 | B |  | 1620 |  |  | FALSE |  | Grade beam labour PO | Dalran Construction | Aubrey Funk | FALSE | FALSE | FALSE |  | 90
1 | 610 | B |  |  |  |  | FALSE |  | Concrete-Grade beam PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 805
1 | 620 | B |  |  |  | 13055 | FALSE |  | Detached garage framing package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 430
1 | 625 | B |  |  |  |  | FALSE |  | Pre-fab wall PO | Igloo Building Supplies | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 351
1 | 630 | B |  |  |  |  | FALSE |  | Main floor package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 400
1 | 640 | B |  |  |  |  | FALSE |  | Second floor and roof package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 410
1 | 650 | B |  |  |  |  | FALSE |  | Framing stairs PO | Sandhills Manufacturing |  | FALSE | FALSE | FALSE |  | 680
1 | 660 | B |  | 2810 |  |  | FALSE |  | House windows/exterior doors PO | Gienow Window & Door | Bruno Salvalaggio | FALSE | FALSE | FALSE |  | 310
1 | 670 | B |  |  |  | 13055 | FALSE |  | Detached garage windows/exterior doors PO | Gienow Building Products (Calgary) |  | FALSE | FALSE | FALSE |  | 311
1 | 680 | B |  |  |  |  | FALSE |  | Framing labour PO | Framer? |  | FALSE | FALSE | FALSE |  | 240
1 | 690 | B |  |  |  |  | FALSE |  | Framing bonus PO | Framer? |  | TRUE | FALSE | FALSE |  | 245
1 | 700 | B |  |  |  | 13055 | FALSE |  | Detached garage framing PO | Framer? |  | FALSE | FALSE | FALSE |  | 246
1 | 710 | B |  |  |  |  | FALSE |  | Deck Package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 460
1 | 720 | B |  |  |  | 53 | FALSE |  | Verandah Package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 461
1 | 730 | B |  |  |  |  | FALSE |  | Deck Framing PO | Trade? |  | FALSE | FALSE | FALSE |  | 190
1 | 740 | B |  |  |  |  | FALSE |  | Aluminum Deck Rails PO | South Side Ornamental |  | FALSE | FALSE | FALSE |  | 740
1 | 750 | B |  |  |  | 700 | FALSE |  | Duradek Surfaces PO | South Side Ornamental |  | FALSE | FALSE | FALSE |  | 50
1 | 760 | B |  | 3760 |  |  | FALSE |  | Tub/Showers PO | Bartle & Gibson | Aubrey Funk | FALSE | FALSE | FALSE |  | 150
1 | 770 | B |  |  |  |  | FALSE |  | House asphalt roofing labour PO | Echo Roofing |  | FALSE | FALSE | FALSE |  | 260
1 | 780 | B |  |  |  | 13055 | FALSE |  | Detached garage asphalt roofing labour PO | Echo Roofing |  | FALSE | FALSE | FALSE |  | 261
1 | 790 | B |  |  |  |  | FALSE |  | House roofing supplies PO | Enercon Roofing |  | FALSE | FALSE | FALSE |  | 270
1 | 800 | B |  |  |  | 13055 | FALSE |  | Detached garage roofing supplies PO | Enercon Roofing |  | FALSE | FALSE | FALSE |  | 271
1 | 810 | B |  |  |  |  | FALSE |  | Plumbing PO | Northgate Plumbing | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 600
1 | 815 | B |  |  |  |  | FALSE |  | Plumbing Extras PO | Northgate Plumbing | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 601
1 | 820 | B |  |  |  |  | FALSE |  | Heating PO | Accent Heating | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 30
1 | 825 | B |  |  |  |  | FALSE |  | Heating Extras PO | Accent Heating | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 31
1 | 830 | B |  | 4330 |  |  | FALSE |  | House pot-lights / undercabinet lighting PO | Park Lighting | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 230
1 | 840 | B |  |  |  | 13055 | FALSE |  | Detached Garage Pot Light PO | Park Lighting | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 231
1 | 850 | B |  |  |  |  | FALSE |  | Lighting Fixtures PO | Park Lighting | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 220
1 | 855 | B |  |  |  |  | FALSE |  | Lighting Extras PO | Park Lighting | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 232
1 | 860 | B |  |  |  |  | FALSE |  | Electrical contractor PO | KJ Electric | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 520
1 | 865 | B |  |  |  |  | FALSE |  | Electrical extras PO | KJ Electric | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 521
1 | 870 | B |  |  |  |  | FALSE |  | Vacuum PO | Readco Industries |  | FALSE | FALSE | FALSE |  | 630
1 | 880 | B |  |  |  |  | FALSE |  | Fireplace supply and install PO | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 300
1 | 890 | B |  |  |  | 121 | FALSE |  | Basement Fireplace Supply and Install PO | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 305
1 | 900 | B |  |  |  |  | FALSE |  | Alarm systems PO | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 500
1 | 910 | B |  |  |  |  | FALSE |  | Sound systems PO | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 505
1 | 920 | B |  |  |  |  | FALSE |  | House siding, soffit and fascia PO | AB Renovations |  | FALSE | FALSE | FALSE |  | 160
1 | 930 | B |  |  |  | 13055 | FALSE |  | Detached garage siding, soffit and fascia PO | AB Renovations |  | FALSE | FALSE | FALSE |  | 161
1 | 940 | B |  |  |  | 73 | FALSE |  | House clad trim PO | AB Renovations |  | FALSE | FALSE | FALSE |  | 20
1 | 950 | B |  |  |  | 13055 | FALSE |  | Detached garage clad trim PO | AB Renovations |  | FALSE | FALSE | FALSE |  | 21
1 | 955 | B |  |  |  |  | FALSE |  | Parging PO | GR Plaster Ltd. |  | FALSE | FALSE | FALSE |  | 315
1 | 960 | B |  |  |  | 56 | FALSE |  | House exterior trim PO | Carpenter/Company? |  | FALSE | FALSE | FALSE |  | 590
1 | 970 | B |  |  |  | 13055 | FALSE |  | Detached garage exterior trim PO | Carpenter/Company>? |  | FALSE | FALSE | FALSE |  | 591
1 | 980 | B |  |  |  |  | FALSE |  | House eavestroughs PO | CW Eavestrough |  | FALSE | FALSE | FALSE |  | 170
1 | 982 | B |  |  |  | 13055 | FALSE |  | Detached garage eavestroughs PO | CW Eavestrough |  | FALSE | FALSE | FALSE |  | 171
1 | 986 | B |  |  |  |  | FALSE |  | Main Insulation Material PO | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 451
1 | 987 | B |  |  |  |  | FALSE |  | Garage Insulation Material PO | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 454
1 | 988 | B |  |  |  |  | FALSE |  | Main Insulation Labour PO |  |  | FALSE | FALSE | FALSE |  | 761
1 | 990 | B |  |  |  |  | FALSE |  | Scaffolding Rental PO | Project Supply Depot Ltd. |  | FALSE | FALSE | FALSE |  | 721
1 | 992 | B |  |  |  |  | FALSE |  | Main Drywall Material PO | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 452
1 | 994 | B |  |  |  |  | FALSE |  | Main Drywall Labour PO | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 86
1 | 996 | B |  |  |  |  | FALSE |  | Main Taping Labour PO | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 851
1 | 998 | B |  |  |  |  | FALSE |  | Basement Insulation Material PO | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 457
1 | 1000 | B |  |  |  |  | FALSE |  | Basement Insulation Labour PO | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 762
1 | 1002 | B |  |  |  |  | FALSE |  | Basement Drywall Material PO | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 453
1 | 1004 | B |  |  |  |  | FALSE |  | Basement Drywall Labour PO | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 87
1 | 1006 | B |  |  |  |  | FALSE |  | Basement Taping Labour PO | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 852
1 | 1008 | B |  |  |  |  | FALSE |  | Main Texture PO | Hennings Texturing |  | FALSE | FALSE | FALSE |  | 341
1 | 1010 | B |  |  |  |  | FALSE |  | Basement Texture PO | Hennings Texturing |  | FALSE | FALSE | FALSE |  | 342
1 | 1012 | B |  |  |  |  | FALSE |  | Attic Blow Insulation PO | Arctic Front Insulation |  | FALSE | FALSE | FALSE |  | 81
1 | 1014 | B |  |  |  | 13117 | FALSE |  | Inslab heating rebar PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 415
1 | 1018 | B |  |  |  |  | FALSE |  | Garage floor sand PO | AC Sand & Gravel Trucking Ltd. |  | FALSE | FALSE | FALSE |  | 25
1 | 1020 | B |  |  |  |  | FALSE |  | Garage floor concrete placing PO | ConTec Concrete |  | FALSE | FALSE | FALSE |  | 655
1 | 1030 | B |  |  |  |  | FALSE |  | Concrete-garage floor PO | Stel-Marr Concrete | Aubrey Funk | FALSE | FALSE | FALSE |  | 780
1 | 1040 | B |  |  |  |  | FALSE |  | Driveway and garage slab rebar PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 425
1 | 1050 | B |  |  |  |  | FALSE |  | Garage doors PO | Overhead Door Company |  | FALSE | FALSE | FALSE |  | 620
1 | 1052 | B |  |  |  |  | FALSE |  | Basement floor sand PO | AC Sand & Gravel Trucking Ltd. |  | FALSE | FALSE | FALSE |  | 27
1 | 1055 | B |  |  |  |  | FALSE |  | Concrete Pumping-Basment floors PO | A&B Concrete Pumping |  | FALSE | FALSE | FALSE |  | 15
1 | 1060 | B |  |  |  |  | FALSE |  | Concrete-basement floor PO | Stel-Marr Concrete | Aubrey Funk | FALSE | FALSE | FALSE |  | 790
1 | 1065 | B |  |  |  |  | FALSE |  | Basement concrete placing PO | ConTec Concrete | Aubrey Funk | FALSE | FALSE | FALSE |  | 650
1 | 1070 | B |  |  |  |  | FALSE |  | Basement development package PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 420
1 | 1080 | B |  |  |  |  | FALSE |  | Basement development framing PO | David Mills |  | FALSE | FALSE | FALSE |  | 200
1 | 1090 | B |  |  |  |  | FALSE |  | Brick-Stone PO | Ancient Stone Works |  | FALSE | FALSE | FALSE |  | 900
1 | 1100 | B |  |  |  |  | FALSE |  | Floor underlay PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 465
1 | 1110 | B |  |  |  |  | FALSE |  | Floor underlay install PO | Carpenter/Company>? |  | FALSE | FALSE | FALSE |  | 468
1 | 1120 | B |  | 5820 |  |  | FALSE |  | Cabinet door order PO | Caron Industries | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 100
1 | 1121 | B |  |  |  |  | FALSE |  | Cabinet door order PO (Basement) | Caron Industries | Rob Salvalaggio | FALSE | FALSE | FALSE
1 | 1130 | B |  | 5820 |  |  | FALSE |  | Cabinet handles PO | Richelieu Hardware | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 637
1 | 1140 | B |  | 7110 |  |  | FALSE |  | Granite counters PO | Allstone Inc. | Aubrey Funk | FALSE | FALSE | FALSE |  | 125
1 | 1145 | B |  |  |  |  | FALSE |  | Granite counter extras PO | Allstone Inc. | Aubrey Funk | FALSE | FALSE | FALSE |  | 126
1 | 1150 | B |  |  |  |  | FALSE |  | Laminate counters PO | Classic Woodcrafting | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 120
1 | 1160 | B |  |  |  |  | FALSE |  | Cabinet installation PO | Millenium Woodwork Ltd |  | FALSE | FALSE | FALSE |  | 290
1 | 1170 | B |  |  |  |  | FALSE |  | Paint supply and labour PO | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 180
1 | 1171 | B |  |  |  |  | FALSE |  | Paint supply and labour-Stage 2 PO | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 182
1 | 1172 | B |  |  |  |  | FALSE |  | Paint supply and labour-Exterior PO | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 187
1 | 1176 | B |  |  |  |  | FALSE |  | Lacquer and prime (first stage spec) PO | Wild Rose Country Painting and Decorating Ltd. |  | TRUE | FALSE | FALSE |  | 185
1 | 1180 | B |  |  |  |  | FALSE |  | Finishing package first PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 470
1 | 1190 | B |  |  |  |  | FALSE |  | Finishing package second PO | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 480
1 | 1200 | B |  | 5510 |  |  | FALSE |  | Interior finishing labour PO | Millenium Woodwork Ltd | Aubrey Funk | FALSE | FALSE | FALSE |  | 580
1 | 1205 | B |  |  |  |  | FALSE |  | Final Stage Interior Finishing PO | Millenium Woodwork Ltd | Aubrey Funk | FALSE | FALSE | FALSE |  | 581
1 | 1210 | B |  |  |  |  | FALSE |  | Stair railings PO | Spindle Factory |  | FALSE | FALSE | FALSE |  | 70
1 | 1220 | B |  |  |  |  | FALSE |  | Floorcoverings-Centura PO | Centura |  | FALSE | FALSE | FALSE |  | 110
1 | 1230 | B |  |  |  |  | FALSE |  | Floorcoverings-Domcor PO | Domcor |  | FALSE | FALSE | FALSE |  | 250
1 | 1240 | B |  |  |  |  | FALSE |  | Floorcoverings-McMahon PO | W.G. McMahon |  | FALSE | FALSE | FALSE |  | 890
1 | 1250 | B |  |  |  |  | FALSE |  | Tile supply-Ames PO | Ames Tile & Stone |  | FALSE | FALSE | FALSE |  | 60
1 | 1260 | B |  |  |  |  | FALSE |  | Tile Supply-Julian PO | Julian Ceramic Tile |  | FALSE | FALSE | FALSE |  | 510
1 | 1270 | B |  |  |  |  | FALSE |  | Hardwood floor supply-TRC PO | TRC Distribution |  | FALSE | FALSE | FALSE |  | 880
1 | 1290 | B |  |  |  |  | FALSE |  | Hardwood floors install PO | Flooring By Henry |  | FALSE | FALSE | FALSE |  | 860
1 | 1300 | B |  |  |  |  | FALSE |  | Tile Installation PO | Stars Tile Contracting Ltd |  | FALSE | FALSE | FALSE |  | 140
1 | 1305 | B |  |  |  |  | FALSE |  | Tile (tub/shower trim only) PO | Stars Tile Contracting Ltd |  | FALSE | FALSE | FALSE |  | 145
1 | 1310 | B |  |  |  |  | FALSE |  | Carpet and lino installation PO | OMT Flooring |  | FALSE | FALSE | FALSE |  | 610
1 | 1320 | B |  |  |  | 77 | FALSE |  | Mirror doors PO | Hallmark Doors Ltd. |  | FALSE | FALSE | FALSE |  | 320
1 | 1330 | B |  |  |  |  | FALSE |  | Mirror and glass PO | Hartwell Glass |  | FALSE | FALSE | FALSE |  | 340
1 | 1335 | B |  |  |  |  | FALSE |  | Cabinet door glass and shelves PO | Hartwell Glass |  | FALSE | FALSE | FALSE |  | 330
1 | 1340 | B |  |  |  |  | FALSE |  | Shower doors PO | Ronco Doors & Distribution |  | FALSE | FALSE | FALSE |  | 640
1 | 1350 | B |  |  |  |  | FALSE |  | Window wells PO | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 540
1 | 1360 | B |  |  |  | 17 | FALSE |  | Pre-Cast Steps PO | CARA Conrete Products |  | FALSE | FALSE | FALSE |  | 760
1 | 1370 | B |  |  |  |  | FALSE |  | Concrete-Steps and porches PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 830
1 | 1380 | B |  |  |  |  | FALSE |  | Concrete-Rear patios PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 835
1 | 1390 | B |  |  |  |  | FALSE |  | Concrete-Sidewalks PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 770
1 | 1400 | B |  |  |  |  | FALSE |  | Concrete-Driveways PO | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 775
1 | 1410 | B |  |  |  |  | FALSE |  | Driveway, sidewalk and landing placement PO | ConTec Concrete |  | FALSE | FALSE | FALSE |  | 660
1 | 1412 | B |  |  |  |  | FALSE |  | RPR-Stantec PO | Stantec |  | FALSE | FALSE | FALSE |  | 793
1 | 1413 | B |  |  |  |  | FALSE |  | RPR-Pals PO | Pals Surveys & Associates Ltd. |  | FALSE | FALSE | FALSE |  | 794
1 | 1414 | B |  |  |  |  | FALSE |  | Grade Staking Stantec PO | Stantec |  | FALSE | FALSE | FALSE |  | 795
1 | 1415 | B |  |  |  |  | FALSE |  | Grade staking Pals PO | Pals Surveys & Associates Ltd. |  | FALSE | FALSE | FALSE |  | 796
1 | 1416 | B |  |  |  |  | FALSE |  | Rough Grade Cert Stantec PO | Stantec |  | FALSE | FALSE | FALSE |  | 797
1 | 1417 | B |  |  |  |  | FALSE |  | Rough Grade Cert Pals PO | Pals Surveys & Associates Ltd. |  | FALSE | FALSE | FALSE |  | 798
1 | 1420 | C | 12 |  |  |  | TRUE | 10 | Schedule Stakeout | Stantec |  | FALSE | FALSE | FALSE |  |  | Schedule Stakeout |  |  |  |  | 1 | [7 empty] | I
1 | 1422 | C | 12 |  |  |  | FALSE |  | Order ICF forms | Salvi Homes | Tara Peters | FALSE | FALSE | FALSE | [7 empty] | 1
1 | 1425 | C | 12 |  |  |  | FALSE |  | Alberta First Call | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1430 | C | 12 |  |  |  | FALSE |  | Check Cut Marks | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1450 | C | 12 | 1610 |  |  | TRUE | 20 | Excavation | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 571 | Schedule Stakeout | 1 | 700 |  |  | 2
1 | 1455 | C | 12 |  |  |  | FALSE |  | Schedule Cribber | Fearon Construction |  | FALSE | FALSE | FALSE |  | 280 | Excavation | 1 | 400 |  |  | 4 | [7 empty] | II
1 | 1456 | C | 12 |  |  |  | FALSE |  | Special Footing Package (Cribbing) | Igloo Building Supplies |  | FALSE | FALSE | FALSE
1 | 1457 | C | 12 |  |  |  | FALSE |  | Piles For Footings | Waytec Enterprises |  | FALSE | FALSE | FALSE |  | 710
1 | 1458 | C | 12 |  |  |  | FALSE |  | Concrete For Special Footing | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 820
1 | 1460 | C | 12 |  |  |  | FALSE |  | Soils Test | Consultech |  | FALSE | FALSE | FALSE
1 | 1470 | C | 12 |  |  |  | FALSE |  | Electrical Trenching | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 570
1 | 1480 | C | 12 |  |  |  | FALSE |  | Plumbing Trenching | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 560
1 | 1490 | C | 12 |  |  |  | FALSE |  | Thaw Ground | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 530
1 | 1530 | C | 12 |  |  | 89 | FALSE |  | Trench for Sump | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 560
1 | 1540 | C | 12 |  |  |  | FALSE |  | Plumbing Pipes | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600
1 | 1570 | C | 12 |  |  |  | FALSE |  | Ground Plate & Pegs | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1575 | C | 12 |  |  |  | FALSE |  | Pump for Footing | A&B Concrete Pumping |  | FALSE | FALSE | FALSE
1 | 1580 | C | 12 | 2510 |  |  | TRUE | 30 | Footing Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 820 | Excavation | 1 |  |  |  | 1
1 | 1585 | C | 12 |  |  |  | FALSE | 35 | Sump Pit Installation | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 535 | Footing Concrete | 1 |  |  |  | 1
1 | 1590 | C | 12 | 1610 |  |  | FALSE |  | Cribbing 1st Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 370 | Footing Concrete | 0 |  |  |  | 1
1 | 1600 | C | 12 | 2515 |  |  | FALSE | 50 | Wall Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 810 | Footing Concrete | 2 |  |  |  | 1
1 | 1610 | C | 12 | 1625 |  |  | FALSE |  | Concrete Pump | A&B Concrete Pumping |  | FALSE | FALSE | FALSE |  | 10
1 | 1620 | C | 12 |  |  |  | FALSE | 55 | Check Walls, Mark Foundation | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Schedule Cribber | 1 |  |  |  | 1
1 | 1630 | C | 12 | 1630 |  |  | TRUE | 60 | Weeping Tile Order | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 530 | Wall Concrete | 3 |  |  |  | 1
1 | 1635 | C | 12 |  |  |  | FALSE | 70 | Basement Gravel | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 536 | Wall Concrete | 3 |  |  |  | 1
1 | 1640 | C | 12 |  |  |  | FALSE | 75 | Footing Inspections | Strathcona County |  | FALSE | FALSE | FALSE |  |  | Weeping Tile Order | 1 |  |  |  | 1
1 | 1670 | C | 12 | 2210 |  |  | FALSE | 100 | Floor Joist Package (2nd Cribbing) | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 380 | Schedule Cribber | 1 |  |  |  | 1
1 | 1680 | C | 12 |  |  |  | FALSE |  | Floor Misc Items (inso,hangers,OSB,poly) | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1700 | C | 12 |  |  |  | FALSE |  | Grade Beam Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 390
1 | 1710 | D | 12 |  |  |  | TRUE | 5 | Order Wood Stairs | Sandhills Manufacturing |  | FALSE | FALSE | FALSE |  | 680 | Backfill | 1 |  |  |  | 1
1 | 1720 | C | 12 |  |  |  | FALSE | 90 | Schedule Floor Framer | David Mills |  | FALSE | FALSE | FALSE |  | 210 | Floor Joist Package (2nd Cribbing) | 0 | 475 |  |  | 3
1 | 1724 | C | 12 | 7620 |  |  | FALSE |  | Clean For Backfill | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Schedule Floor Framer | -1 |  |  |  | 1
1 | 1725 | C | 12 | 1610 |  |  | FALSE | 80 | Backfill | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  | 572 | Schedule Floor Framer | 1 |  |  |  | 1 | [7 empty] | IIII
1 | 1730 | C | 12 |  |  |  | FALSE |  | Basement & Site Clean up | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1740 | C | 12 |  |  |  | FALSE |  | Mark Piles | Kulka Enterprises Inc |  | FALSE | FALSE | FALSE |  | 280
1 | 1750 | C | 12 |  |  |  | FALSE |  | Place piles for verandah/decks | Kulka Enterprises Inc |  | FALSE | FALSE | FALSE |  | 280
1 | 1760 | C | 12 | 1650 |  |  | FALSE | 120 | Drill Piles | Waytec Enterprises |  | FALSE | FALSE | FALSE |  | 710 | Backfill | 1 |  |  |  | 1
1 | 1770 | C | 12 |  |  |  | FALSE | 130 | Piles Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 800 | Backfill | 1 |  |  |  | 1
1 | 1780 | C | 12 |  |  |  | FALSE |  | Pour pile caps | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1784 | C | 12 |  |  |  | FALSE |  | Grade Beam Cribber | Kulka Enterprises Inc |  | FALSE | FALSE | FALSE |  | 280 | Drill Piles | 0 |  |  |  | 3
1 | 1786 | C | 12 |  |  |  | FALSE |  | Pump for grade beam | A&B Concrete Pumping |  | FALSE | FALSE | FALSE
1 | 1790 | C | 12 | 2520 |  |  | TRUE | 140 | Grade Beam Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 805 | Drill Piles | 1 |  |  |  | 1 | [7 empty] | IIIIIIIII
1 | 1800 | F | 12 | 2541 |  | 17 | FALSE |  | Mark and order pre-cast steps | Burnco |  | FALSE | FALSE | FALSE |  | 760
1 | 1810 | C | 12 |  |  |  | FALSE |  | Mark Grade Beam | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Grade Beam Concrete | 1 |  |  |  | 1
1 | 1820 | C | 123 |  |  |  | FALSE | 150 | Backfill Grade Beam | Exact Excavating Inc. |  | FALSE | FALSE | FALSE |  |  | Grade Beam Concrete | 2 |  |  |  | 1
1 | 1830 | D | 12 |  |  |  | TRUE | 10 | Gas Line Site Inspection | Atco Gas |  | FALSE | FALSE | FALSE |  | 80 | Backfill Grade Beam | 1 |  |  |  | 1
1 | 1840 | D | 12 |  |  |  | FALSE |  | Gas Line Site Installation (N.W.U.) | Atco Gas |  | FALSE | FALSE | FALSE |  | 80 | Gas Line Site Inspection | 10 |  |  |  | 1
1 | 1843 | D | 12 |  |  |  | FALSE |  | Prep for Panel | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1844 | D | 12 |  |  |  | TRUE | 20 | Order Electrical Panel | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Backfill | 1 |  |  |  | 1
1 | 1845 | D | 12 |  |  |  | TRUE | 30 | Power Meter | EPCOR Energy Services Inc. |  | FALSE | FALSE | FALSE |  |  | Order Electrical Panel | 2 |  |  |  | 1
1 | 1847 | D | 12 |  |  |  | TRUE | 40 | Framing Package #1 | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 400 | Backfill | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIII
1 | 1848 | D | 134 |  |  |  | TRUE | 100 | Deck Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 460 | Framing Package #1 | 0 |  |  |  | 1
1 | 1849 | D | 134 |  |  |  | FALSE |  | Deck Framing | Trade??? |  | FALSE | FALSE | FALSE |  | 190
1 | 1850 | D | 134 |  |  |  | FALSE |  | Deck Railing & Steps | Igloo Building Supplies |  | FALSE | FALSE | FALSE
1 | 1852 | D | 12 |  |  | 53 | TRUE | 110 | Verandah Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 461 | Framing Package #1 | 0 |  |  |  | 1
1 | 1853 | D | 12 |  |  | 53 | FALSE |  | Frame verandah | Trade??? |  | FALSE | FALSE | FALSE |  | 190
1 | 1870 | D | 12 |  |  |  | TRUE | 50 | Schedule Main Framer | Salvi Homes |  | FALSE | FALSE | FALSE |  | 240 | Framing Package #1 | 0 |  |  |  | 15 | [7 empty] | IIIIIIIIIIIIIII
1 | 1880 | D | 12 |  |  |  | FALSE |  | Place Temporary Sidewalks | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1885 | D | 12 |  |  |  | FALSE |  | Deliver Main Wall Panels | Igloo Building Supplies |  | FALSE | FALSE | FALSE
1 | 1895 | D | 12 |  |  |  | FALSE |  | House Misc Items (tyvek,hangers,inso,OSB) | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1897 | D | 12 |  |  |  | TRUE | 60 | Framing Package #2 | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 410 | Framing Package #1 | 2 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIII
1 | 1925 | D | 12 |  |  |  | TRUE | 70 | Roof Truss Delivery | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 360 | Framing Package #1 | 2 |  |  |  | 1
1 | 1927 | D | 12 |  |  |  | FALSE |  | Deliver 2nd Pre-Fab Panels | Igloo Building Supplies |  | FALSE | FALSE | FALSE
1 | 1935 | D | 12 |  |  |  | TRUE | 90 | Window Delivery | Gienow Window & Door |  | FALSE | FALSE | FALSE |  | 310 | Schedule Main Framer | -3 |  |  |  | 1
1 | 1937 | D | 12 |  |  |  | FALSE |  | Order custom range hood vent | Trail Appliances |  | FALSE | FALSE | FALSE |  |  | Schedule Main Framer | -3 |  |  |  | 1 | [6 empty] | To Salvi Shop
1 | 1940 | D | 124 |  |  |  | FALSE |  | Confirm Cabinets Layout | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1950 | E | 12 |  |  |  | TRUE | 10 | Insulate Fireplace & Showers | Drywall Company?? |  | FALSE | FALSE | FALSE |  | 40 | Schedule Main Framer | -3 |  |  |  | 1
1 | 1960 | D | 12 |  |  |  | FALSE |  | Whirlpool/Soaker Tub Framing | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 1970 | E | 12 |  |  |  | TRUE | 20 | Fiberglass Tub/Shower Delivery | Bartle & Gibson |  | FALSE | FALSE | FALSE |  | 150 | Insulate Fireplace & Showers | 1 |  |  |  | 1
1 | 1980 | E | 12 |  |  |  | TRUE | 25 | Mark Heating holes & flashing | Accent Heating |  | FALSE | FALSE | FALSE |  | 30 | Schedule Main Framer | -4 |  |  |  | 1
1 | 1991 | F | 12 |  |  | 56 | TRUE | 10 | Measure painted Trim | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Framing Check | 0 |  |  |  | 1
1 | 1992 | F | 13 |  |  | 56 | TRUE | 20 | Cut and paint trim | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Measure painted Trim | 3 |  |  |  | 1
1 | 1993 | F | 13 |  |  | 53 | TRUE | 30 | Install Columns and trim | Salvi Homes |  | FALSE | FALSE | FALSE |  | 190 | Cut and paint trim | 1 |  |  |  | 2
1 | 1995 | D | 12 |  |  |  | FALSE |  | Screw Pocket Door Hardware | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2000 | d | 12 |  |  |  | FALSE |  | House Framing Inspection | Strathcona County |  | FALSE | FALSE | FALSE
1 | 2010 | D | 12 |  |  |  | FALSE |  | Site Clean Up | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2020 | D | 12 |  |  |  | FALSE |  | Move good material | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2025 | D |  |  |  |  | FALSE |  | Railing Measure and frame check | Spindle Factory |  | FALSE | FALSE | FALSE
1 | 2030 | E | 12 |  |  |  | FALSE |  | Lock Doors | Millenium Woodwork Ltd |  | FALSE | FALSE | FALSE |  | 580
1 | 2035 | E | 12 |  |  |  | FALSE |  | Signage | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2040 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage stakeout | Pals Surveys & Associates Ltd. |  | FALSE | FALSE | FALSE
1 | 2050 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage excavation | Exact Excavating Inc. |  | FALSE | FALSE | FALSE
1 | 2055 | Z | 13 |  |  |  | FALSE |  | Detached Garage Pad Forming | Rockhead Construction |  | FALSE | FALSE | FALSE
1 | 2060 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 780
1 | 2070 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage roof truss order | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 365
1 | 2080 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage framing package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 430
1 | 2090 | Z | 13 |  |  | 13055 | FALSE |  | Detached garage framing | Framer>? |  | FALSE | FALSE | FALSE |  | 246
1 | 2100 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Windows/Doors | Gienow Building Products (Calgary) |  | FALSE | FALSE | FALSE |  | 311
1 | 2110 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Roofing Material | Enercon Roofing |  | FALSE | FALSE | FALSE |  | 271
1 | 2120 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Roofing Labour | Echo Roofing |  | FALSE | FALSE | FALSE |  | 261
1 | 2130 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Electrical | KJ Electric |  | FALSE | FALSE | FALSE |  | 520
1 | 2140 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Siding,Soffit,Fascia | AB Renovations |  | FALSE | FALSE | FALSE |  | 161
1 | 2150 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Eavestrough | CW Eavestrough |  | FALSE | FALSE | FALSE |  | 171
1 | 2160 | Z | 13 |  |  | 13055 | FALSE |  | Detached Garage Clad Trim | AB Renovations | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 21
1 | 2242 | F | 14 |  |  | 53 | FALSE |  | Frame verandah steps, railing and skirting | Trade??? |  | FALSE | FALSE | FALSE |  | 190
1 | 2245 | D | 12 |  |  |  | TRUE | 120 | Framing Check | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Schedule Main Framer | 1 |  |  |  | 1
1 | 2246 | F | 13 |  |  | 590 | FALSE |  | Garage Sump | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600
1 | 2247 | D | 14 |  |  |  | FALSE |  | Interior Railing Take-Off | Spindle Factory |  | FALSE | FALSE | FALSE |  | 700
1 | 2247 | F | 13 |  |  |  | TRUE | 40 | Sand for Garage | AC Sand & Gravel Trucking Ltd. |  | FALSE | FALSE | FALSE |  |  | Plumbing Rough-In | 1 |  |  |  | 1
1 | 2248 | F | 13 | 2535 |  |  | TRUE | 50 | Garage Floor Concrete | Rockhead Construction |  | FALSE | FALSE | FALSE |  | 780 | Sand for Garage | 1 |  |  |  | 1
1 | 2290 | E | 13 | 3420 |  |  | TRUE | 30 | Fireplace Installation | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 300 | Schedule Main Framer | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIII
1 | 2300 | E | 13 |  |  |  | TRUE | 35 | Basement Fireplace Vent | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 305
1 | 2320 | E | 13 | 3710 |  |  | TRUE | 40 | Plumbing Rough-In | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Schedule Main Framer | 1 | 700 |  |  | 3 | [7 empty] | IIIIIIIIIIIIIIIII
1 | 2330 | E | 123 | 4020 |  |  | TRUE | 50 | Heating Rough-In | Accent Heating |  | FALSE | FALSE | FALSE |  | 30 | Plumbing Rough-In | 0 | 1200 |  |  | 2
1 | 2335 | F | 13 |  |  |  | TRUE | 70 | Roofing Material | Enercon Roofing |  | FALSE | FALSE | FALSE |  | 270 | Schedule Main Framer | 0 |  |  |  | 1
1 | 2340 | F | 13 |  |  |  | TRUE | 75 | Roofing Labour | Echo Roofing | Aubrey Funk | FALSE | FALSE | FALSE |  | 260 | Roofing Material | 1 |  |  |  | 4
1 | 2355 | F | 13 |  |  |  | FALSE |  | Install Skylights | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2370 | E | 13 |  |  |  | TRUE | 55 | Gas Line Plumber | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Heating Rough-In | 1 |  |  |  | 1
1 | 2375 | H | 13 |  |  |  | FALSE |  | Main Inso, Board & Tape Takeoff | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Plumbing Rough-In | -1 |  |  |  | 1
1 | 2380 | E | 13 |  |  |  | TRUE | 60 | Electrical Walk-Through | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Heating Rough-In | 1 |  |  |  | 1
1 | 2385 | E | 13 |  |  |  | FALSE |  | Pot Light Can Delivery | Salvi Homes |  | FALSE | FALSE | FALSE |  | 230 | Electrical Walk-Through | 0 |  |  |  | 1
1 | 2390 | E | 13 | 4310 |  |  | TRUE | 70 | Electrical Rough-In | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Electrical Walk-Through | 1 | 700 |  |  | 2 | [7 empty] | IIIIIIIIIIIIIIIIIIIII
1 | 2400 | E | 13 | 4610 |  |  | TRUE | 80 | Vacuum Rough-In | Readco Industries |  | FALSE | FALSE | FALSE |  | 630 | Electrical Rough-In | 0 |  |  |  | 1
1 | 2410 | E | 13 | 4625 |  |  | TRUE | 90 | Security System Rough In | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 500 | Electrical Rough-In | 0 |  |  |  | 1
1 | 2420 | E | 13 |  |  |  | TRUE | 100 | Sound System Rough In | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 505 | Electrical Rough-In | 0 |  |  |  | 1
1 | 2425 | E | 13 |  |  |  | FALSE |  | Tarp Basement | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2435 | D | 13 |  |  |  | FALSE |  | Site & House Clean Up | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2437 | F | 13 |  |  |  | FALSE |  | Tarp for step concrete | Rockhead Construction |  | FALSE | FALSE | FALSE
1 | 2440 | F | 13 |  |  |  | TRUE | 80 | Step concrete Labour | Rockhead Construction |  | FALSE | FALSE | FALSE |  |  | Roofing Labour | 1 |  |  |  | 3
1 | 2445 | F | 13 | 2540 |  | 35 | TRUE | 90 | Step Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 830 | Roofing Labour | 2 |  |  |  | 1
1 | 2447 | F | 13 |  |  |  | TRUE | 100 | Pre-rough grade | Salvi Homes |  | FALSE | FALSE | FALSE |  | 574 | Step Concrete | 2 |  |  |  | 1
1 | 2448 | F | 12 | 1635 |  |  | FALSE |  | Window Wells | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 540
1 | 2449 | F | 12 |  |  |  | FALSE |  | Window Wells Gravel | Lenbeth Weeping Tile |  | FALSE | FALSE | FALSE |  | 540
1 | 2450 | F | 13 |  |  |  | FALSE |  | Schedule bricklayer | Ancient Stone Works |  | FALSE | FALSE | FALSE |  | 900 | Roofing labour | 1 |  |  |  | 2
1 | 2465 | F | 134 |  |  | 700 | FALSE |  | Deck Vinyl | SunGuard Alberta | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 50
1 | 2470 | F | 13 |  |  |  | TRUE | 110 | Siding and soffit | AB Renovations |  | FALSE | FALSE | FALSE |  | 160 | Electrical Rough-In | 2 | 230 |  |  | 5 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 2471 | H | 13 |  |  |  | FALSE |  | Scaffold delivery | Salvi Homes |  | FALSE | FALSE | FALSE |  | 721
1 | 2472 | H | 13 |  |  |  | FALSE |  | Order Main Insulation Material | Igloo Drywall Distribution |  | FALSE | FALSE | FALSE |  | 451 | Electrical Rough-In | 1 |  |  |  | 1
1 | 2475 | F | 134 |  |  | 73 | FALSE |  | Cladding | AB Renovations | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 20
1 | 2490 | F | 13 | 5220 |  |  | TRUE | 120 | Eavestrough | CW Eavestrough | Aubrey Funk | FALSE | FALSE | FALSE |  | 170 | Siding and soffit | 1 |  |  |  | 1
1 | 2491 | F | 134 |  |  |  | FALSE |  | Metal or Glass Deck Rail | South Side Ornamental | Rob Salvalaggio | FALSE | FALSE | FALSE |  | 740
1 | 2500 | M |  |  |  |  | FALSE |  | Finalize details & get customer approval | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 2500 | H |  |  |  |  | FALSE |  | Spray foam insulation | Atomik Spray Systems |  | FALSE | FALSE | FALSE |  | 1507
1 | 2510 | M |  |  |  |  | FALSE |  | Sign off colour choice | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 2520 | M |  |  |  |  | FALSE |  | Change Order & Memo to trades | Bruno Salvalaggio | Bruno Salvalaggio | FALSE | FALSE | FALSE
1 | 2530 | J |  |  |  |  | FALSE |  | Final Takeoffs & material order (Carpet…Tile…..) | Rob Salvalaggio | Rob Salvalaggio | FALSE | FALSE | FALSE |  |  | Framing Check | 0 |  |  |  | 2
1 | 2540 | J |  |  |  |  | FALSE |  | Update website specs / pricing | Rob Salvalaggio |  | FALSE | FALSE | FALSE |  |  | Final Takeoffs & material order (Carpet…Tile…..) | 1 |  |  |  | 1
1 | 2600 | H | 13 |  |  |  | FALSE |  | Sweep For Insulation | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Electrical Rough-In | 1 |  |  |  | 1
1 | 2610 | H | 13 |  |  |  | TRUE | 10 | Insulation | Card Contracting Ltd. |  | FALSE | FALSE | FALSE |  | 761 | Sweep For Insulation | 1 | 700 |  |  | 2 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIII
1 | 2620 | H | 13 |  |  |  | FALSE |  | Insulation Inspection | Strathcona County |  | FALSE | FALSE | FALSE |  |  | Insulation | 1 |  |  |  | 1
1 | 2630 | H | 13 |  |  |  | FALSE |  | Order Main Board Material | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 452 | Main Inso, Board & Tape Takeoff | 1 |  |  |  | 1
1 | 2650 | D | 134 |  |  |  | FALSE |  | Screw Stairs | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2660 | E | 13 |  |  |  | FALSE |  | Gas Meter | Atco Gas |  | FALSE | FALSE | FALSE
1 | 2670 | G | 13 |  |  |  | FALSE | 10 | Connect Furnace | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2680 | H | 13 | 4910 |  |  | TRUE | 20 | Drywall | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 86 | Insulation Inspection | 1 | 400 | 750 | 4926 | 3 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIII
1 | 2690 | H | 13 |  |  |  | TRUE | 30 | Attic Insulation | Arctic Front Insulation |  | FALSE | FALSE | FALSE |  | 81 | Drywall | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 2700 | H | 13 |  |  |  | FALSE |  | Pickup Main Board Garbage | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2705 | H | 13 |  |  |  | FALSE |  | Pickup Main Extra Inso & Board | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2710 | G | 13 |  |  |  | TRUE | 20 | Plumbing Ground Work | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Plumbing Rough-In | 0 |  |  |  | 1
1 | 2720 | G | 13 |  |  | 13117 | FALSE |  | Poly B Slab Heating | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Plumbing Ground Work | 0 |  |  |  | 2
1 | 2730 | G | 13 |  |  |  | FALSE |  | Sand in Basement | AC Sand & Gravel Trucking Ltd. |  | FALSE | FALSE | FALSE |  |  | Plumbing Ground Work | 1 |  |  |  | 1
1 | 2735 | G | 13 |  |  |  | FALSE |  | Spread gravel for basement | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Plumbing Ground Work | 1 |  |  |  | 1
1 | 2740 | G | 13 |  |  |  | FALSE |  | Level Telepost | ConTec Concrete |  | FALSE | FALSE | FALSE |  | 650
1 | 2750 | G | 13 |  |  |  | FALSE |  | Hilti basement walls | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2785 | G | 13 |  |  |  | FALSE |  | Concrete Pump For Basment | A&B Concrete Pumping |  | FALSE | FALSE | FALSE |  |  | Plumbing Ground Work | 3 |  |  |  | 1
1 | 2790 | G | 13 | 2525 |  |  | TRUE | 30 | Basement floor concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 790 | Plumbing Ground Work | 3 |  |  |  | 1
1 | 2795 | G |  |  |  |  | FALSE | 31 | Basement floor concrete labour | Rockhead Construction |  | FALSE | FALSE | FALSE |  | 650 | Plumbing Ground Work | 3
1 | 2805 | H | 13 |  |  |  | FALSE |  | Garage Inso, Board & Tape Takeoff | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2815 | H | 13 |  |  |  | FALSE |  | Order Garage Insulation | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 454
1 | 2820 | H | 13 |  |  |  | TRUE | 32 | Garage Insulation | Card Contracting Ltd. |  | FALSE | FALSE | FALSE |  | 611 | Garage Floor Concrete | 2 |  |  |  | 1
1 | 2822 | H | 13 |  |  |  | FALSE |  | Garage insulation inspection | Strathcona County |  | FALSE | FALSE | FALSE
1 | 2825 | H | 13 |  |  |  | FALSE |  | Order Garage Drywall | Consolidated Gypsum |  | FALSE | FALSE | FALSE |  | 456
1 | 2830 | H | 13 |  |  |  | TRUE | 33 | Garage Drywall | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 88 | Garage Insulation | 1 |  |  |  | 1
1 | 2833 | H | 13 |  |  |  | FALSE |  | Pickup Garage Board Garbage | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2834 | H | 13 |  |  |  | FALSE |  | Pickup Garage Extra Inso & Board | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2835 | E | 13 |  |  | 653 | FALSE |  | Install garage furnace | Accent Heating |  | FALSE | FALSE | FALSE |  | 30
1 | 2840 | H | 13 |  |  |  | TRUE | 34 | Garage Taping | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 851 | Garage Drywall | 1 |  |  |  | 1
1 | 2845 | F | 13 | 2840 |  |  | TRUE | 60 | Garage Door | Overhead Door Company |  | FALSE | FALSE | FALSE |  | 620 | Garage Drywall | 2 |  |  |  | 1
1 | 2850 | H | 13 |  |  |  | FALSE |  | Garage Priming | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 180
1 | 2860 | H | 13 |  |  |  | FALSE |  | Frame Garage steps | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2870 | G | 13 |  |  | 121 | TRUE | 40 | Basement Heating Duct Work | Accent Heating |  | FALSE | FALSE | FALSE |  | 30 | Basement floor concrete | 2 | 500 |  |  | 3
1 | 2880 | F | 123 |  |  |  | FALSE |  | Check C.C. | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2890 | G | 13 |  |  |  | FALSE |  | Basement X-Bridging |  |  | TRUE | FALSE | FALSE
1 | 2900 | G | 13 |  |  | 137 | FALSE |  | Clean Basement for Steel Studs | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2910 | G | 13 |  |  | 137 | FALSE |  | Basement Frame Metal Studs | Drywall Company?? |  | TRUE | FALSE | FALSE |  | 40
1 | 2920 | F | 13 |  |  |  | FALSE |  | RPR (After Deck) |  | Tara Peters | FALSE | FALSE | FALSE
1 | 2930 | H | 13 | 4910 |  |  | TRUE | 40 | Taping | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 851 | Drywall | 1 | 340 | 550 | 4930 | 5 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 2940 | H | 13 |  |  |  | FALSE |  | Sweep For Priming/Deliver Garbage Cans | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2950 | H | 13 | 6110 |  |  | TRUE | 50 | Priming | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 180 | Taping | 2 |  |  |  | 1
1 | 2970 | H | 134 | 4910 |  |  | TRUE | 60 | Texture ceilings | Hennings Texturing |  | FALSE | FALSE | FALSE |  | 341 | Priming | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 2975 | H | 13 |  |  |  | FALSE |  | Return Scaffold | Salvi Homes |  | FALSE | FALSE | FALSE |  | 721
1 | 2980 | H | 13 |  |  |  | FALSE |  | Light Check | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 2990 | I | 134 |  |  |  | TRUE | 10 | Temp Lighting | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Texture ceilings | 1 |  |  |  | 1
1 | 3000 | J | 14 |  |  |  | FALSE |  | Carpet underlay delivery | W.G. McMahon |  | FALSE | FALSE | FALSE |  | 890
1 | 3010 | J | 14 |  |  |  | FALSE |  | Carpet Delivery | W.G. McMahon |  | FALSE | FALSE | FALSE |  | 890
1 | 3020 | J | 14 |  |  |  | FALSE |  | Carpet Delivery | Centura |  | FALSE | FALSE | FALSE |  | 110
1 | 3030 | J | 14 |  |  |  | FALSE |  | Lino Delivery | W.G. McMahon |  | FALSE | FALSE | FALSE |  | 890
1 | 3040 | J | 14 |  |  |  | FALSE |  | Lino Delivery | Centura |  | FALSE | FALSE | FALSE |  | 110
1 | 3050 | J | 14 |  |  |  | FALSE |  | Lino Delivery | Domcor |  | FALSE | FALSE | FALSE |  | 250
1 | 3060 | J | 14 |  |  | 502 | FALSE |  | Laminate underpad delivery | Domcor |  | FALSE | FALSE | FALSE |  | 250
1 | 3070 | J | 14 |  |  | 502 | FALSE |  | Laminate delivery | Domcor |  | FALSE | FALSE | FALSE |  | 250
1 | 3075 | J | 14 |  |  | 502 | FALSE |  | Laminate delivery | Centura |  | FALSE | FALSE | FALSE |  | 110
1 | 3080 | J | 14 |  |  |  | FALSE |  | Ceramic Tile Delivery | Ames Tile & Stone |  | FALSE | FALSE | FALSE |  | 60
1 | 3090 | J | 14 |  |  |  | FALSE |  | Ceramic Tile Delivery | Centura |  | FALSE | FALSE | FALSE |  | 110
1 | 3100 | J | 14 |  |  |  | FALSE |  | Ceramic Tile Delivery | Julian Ceramic Tile |  | FALSE | FALSE | FALSE |  | 510
1 | 3110 | J | 14 |  |  |  | FALSE |  | Hardwood Floor Delivery | TRC Distribution |  | FALSE | FALSE | FALSE |  | 880
1 | 3130 | I | 14 |  |  |  | TRUE | 20 | Plywood underlay delivery | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 465 | Texture ceilings | 0 |  |  |  | 1
1 | 3140 | I | 14 |  | 1 |  | FALSE |  | Install Underlay | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Plywood underlay delivery | 1 |  |  |  | 1
1 | 3142 | I | 14 |  |  |  | FALSE |  | Screw stair check | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3143 | G | 13 |  |  |  | FALSE |  | Nail & Caulk Basement Windows | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3145 | I | 14 |  |  |  | FALSE |  | Sweep for cabinets | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3150 | I | 14 |  |  |  | FALSE |  | Closet Organizers | Aubrey Funk | Aubrey Funk | FALSE | FALSE | FALSE
1 | 3155 | I | 134 |  |  |  | FALSE |  | Finishing material takeoff | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3160 | G | 13 |  |  |  | TRUE | 50 | Basement Framing Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 420 | Basement Heating Duct Work | 0 |  |  |  | 1
1 | 3170 | G | 13 |  |  |  | TRUE | 60 | Basement framer | Trade??? |  | FALSE | FALSE | FALSE |  | 200 | Basement Framing Package | 1 | 250 |  |  | 2
1 | 3180 | I | 134 |  |  | 121 | FALSE |  | Basement Cabinet Layout | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3190 | G | 13 |  |  | 121 | FALSE |  | Basement Frame Check | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3200 | G | 13 |  |  | 121 | FALSE |  | Basement Insulate Fireplace & Showers | Drywall Company?? |  | FALSE | FALSE | FALSE |  | 40
1 | 3210 | G | 13 |  |  | 121 | FALSE |  | Basement Tub Delivery | Bartle & Gibson |  | FALSE | FALSE | FALSE |  | 150
1 | 3220 | G | 13 |  |  | 121 | FALSE |  | Basement Fireplace Installation | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 300
1 | 3230 | G | 13 |  |  | 121 | TRUE | 70 | Basement Heating-Finish | Accent Heating |  | FALSE | FALSE | FALSE |  | 30 | Basement framer | 1 |  |  |  | 1
1 | 3240 | G | 13 |  |  | 121 | TRUE | 80 | Basement Plumbing | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Basement Heating-Finish | 0 |  |  |  | 1
1 | 3245 | G | 13 |  |  |  | FALSE |  | Basement Inso, Board & Tape Takeoff | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3250 | G | 13 |  |  | 121 | TRUE | 90 | Basement Electrical Walk-Through | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Basement Plumbing | 0 |  |  |  | 1
1 | 3255 | G | 13 |  |  |  | FALSE |  | Basement Pot Light Can Delivery | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Basement Electrical Walk-Through | 0 |  |  |  | 1
1 | 3260 | G | 13 |  |  | 121 | TRUE | 100 | Basement Electrical Rough-In | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Basement Electrical Walk-Through | 1 | 700 |  |  | 2
1 | 3270 | G | 13 |  |  | 121 | FALSE |  | Basement Vac RTL | Readco Industries |  | FALSE | FALSE | FALSE |  | 630 | Basement Electrical Walk-Through | 2 |  |  |  | 1
1 | 3280 | G | 13 |  |  | 121 | FALSE |  | Basement Security RTL | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 500 | Basement Electrical Walk-Through | 2 |  |  |  | 1
1 | 3290 | G | 13 |  |  | 121 | FALSE |  | Basement sound RTL | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 500 | Basement Electrical Walk-Through | 2 |  |  |  | 1
1 | 3295 | G | 13 |  |  |  | FALSE |  | Order Basement Insulation Material | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 457
1 | 3300 | G | 13 |  |  |  | FALSE |  | Sweep Basement for Insulation | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Basement Electrical Rough-In | 1 |  |  |  | 1
1 | 3310 | G | 13 |  |  |  | TRUE | 110 | Basement Insulation | Drywall Company?? |  | FALSE | FALSE | FALSE |  | 762 | Sweep Basement for Insulation | 1 | 1000 |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3320 | G | 13 |  |  |  | FALSE |  | Basement Insulation Inspection | Strathcona County |  | FALSE | FALSE | FALSE
1 | 3325 | G | 13 |  |  |  | FALSE |  | Order Basement Board Material | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 453
1 | 3330 | G | 13 |  |  | 121 | TRUE | 120 | Basement drywall | Drywall Company?? |  | FALSE | FALSE | FALSE |  | 87 | Basement Insulation | 2 | 400 |  |  | 3 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3345 | G | 13 |  |  |  | FALSE |  | Pickup Basement Board Garbage | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3346 | G | 13 |  |  |  | FALSE |  | Pickup Basement Extra Inso & Board | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3350 | G | 13 |  |  | 121 | TRUE | 130 | Basement Tape | Drywall Company?? |  | FALSE | FALSE | FALSE |  | 852 | Basement drywall | 1 | 340 |  |  | 5 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3360 | G | 13 |  |  | 121 | FALSE |  | Sweep Basement For Priming | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3370 | G | 13 |  |  | 121 | TRUE | 140 | Basement Prime | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 180 | Basement Tape | 2 |  |  |  | 1
1 | 3380 | G | 134 |  |  | 121 | TRUE | 150 | Basement Texture | Hennings Texturing |  | FALSE | FALSE | FALSE |  | 341 | Basement Prime | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3390 | G | 13 |  |  | 121 | FALSE |  | Basement light check | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3400 | I | 134 |  |  | 121 | FALSE |  | Basement Lighting | KJ Electric |  | FALSE | FALSE | FALSE |  | 520
1 | 3430 | F | 14 | 5230 |  |  | FALSE |  | Parging | GR Plaster Ltd. |  | FALSE | FALSE | FALSE
1 | 3440 | F | 14 | 6115 |  |  | FALSE |  | Exterior trim painting | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 187
1 | 3450 | F | 14 |  |  |  | FALSE |  | Prep deck and verandah for paint | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 187
1 | 3460 | F | 14 |  |  | 53 | FALSE |  | Verandah Painting | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 187
1 | 3470 | F | 14 |  |  |  | FALSE |  | Deck Painting | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 187
1 | 3490 | F | 134 |  |  |  | FALSE |  | Grade Stake |  |  | FALSE | FALSE | FALSE
1 | 3500 | F | 134 |  |  |  | FALSE |  | Cut Driveway | Rockhead Construction |  | FALSE | FALSE | FALSE
1 | 3510 | F | 134 | 0 |  |  | FALSE |  | Driveway Forming & Sand | Rockhead Construction |  | FALSE | FALSE | FALSE |  | 660
1 | 3520 | F | 134 |  |  |  | TRUE | 130 | Driveway Concrete | Rockhead Construction |  | FALSE | FALSE | FALSE |  | 775
1 | 3540 | F | 134 |  |  |  | FALSE |  | Sidewalk Forming & Sand | Rockhead Construction |  | FALSE | FALSE | FALSE |  | 660
1 | 3550 | F | 134 | 2545 |  |  | TRUE | 140 | Sidewalk Concrete | Stel-Marr Concrete |  | FALSE | FALSE | FALSE |  | 770
1 | 3560 | F | 14 |  |  |  | FALSE |  | Rough Grading | Stantec |  | FALSE | FALSE | FALSE |  | 576
1 | 3570 | F | 14 | 7310 |  |  | FALSE |  | Rough Grading Inspections | Strathcona County |  | FALSE | FALSE | FALSE
1 | 3580 | F | 14 |  |  | 628 | FALSE |  | Address Post | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3590 | F | 14 |  |  |  | FALSE |  | Black Dirt |  |  | TRUE | FALSE | FALSE
1 | 3600 | F | 14 |  |  |  | FALSE |  | Grading Certificate (Black Dirt) | Stantec |  | TRUE | FALSE | FALSE
1 | 3620 | J | 14 | 6750 | 10 |  | FALSE |  | Site Finsh Hardwood Install | 152229 Alberta Inc. |  | FALSE | FALSE | FALSE |  | 860
1 | 3630 | I | 14 |  | 20 |  | TRUE | 30 | Railing Installation | Spindle Factory |  | FALSE | FALSE | FALSE |  | 70 | Texture ceilings | 1 |  | 1400 | 5515 | 1
1 | 3645 | I | 14 |  | 5 |  | TRUE | 50 | Cabinet fabrication | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Taping | -4 |  |  |  | 5
1 | 3650 | I | 14 | 5525 | 30 |  | TRUE | 60 | Cabinet Installation | Millenium Woodwork Ltd |  | FALSE | FALSE | FALSE |  | 290 | Install Underlay | 1 |  | 600 | 5525 | 3
1 | 3660 | I | 14 |  |  |  | FALSE |  | Sweep House & Empty Garbage | Salvi Homes |  | FALSE | FALSE | FALSE
1 | 3670 | I | 14 | 5810 | 35 |  | TRUE | 70 | 1st Finishing Package- IGLOO | Igloo Building Supplies | Aubrey Funk | FALSE | FALSE | FALSE |  | 470 | Cabinet Installation | -2 |  |  |  | 1
1 | 3680 | I | 14 |  |  |  | TRUE | 80 | 1st Finishing Package- SALVI | Salvi Homes | Aubrey Funk | FALSE | FALSE | FALSE |  |  | Cabinet Installation | -2 |  |  |  | 1
1 | 3690 | I | 14 |  | 40 |  | TRUE | 90 | Finishing Carpenter 1st | Millenium Woodwork Ltd |  | FALSE | FALSE | FALSE |  | 580 | Cabinet Installation | -1 | 680 |  |  | 3 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3691 | I | 14 |  | 45 |  | FALSE |  | Deliver sinks in granite to Salvi | Northgate Plumbing |  | FALSE | FALSE | FALSE |  |  | Cabinet Installation | 0 |  |  |  | 1 | [6 empty] | Kitchen sink only?
1 | 3693 | I | 14 | 0 | 50 |  | FALSE |  | Laminate Top Measure | Classic Woodcrafting |  | FALSE | FALSE | FALSE |  | 120 | Cabinet Installation | 1 |  |  |  | 1
1 | 3694 | I | 14 |  | 60 |  | FALSE |  | Granite counter measure | Allstone Inc. |  | FALSE | FALSE | FALSE |  | 125 | Cabinet Installation | 1 |  |  |  | 1
1 | 3695 | I | 14 |  | 70 |  | TRUE | 95 | Fireplace Stone | Ancient Stone Works |  | FALSE | FALSE | FALSE |  | 900 | Finishing Carpenter 1st | 1 |  |  |  | 1
1 | 3698 | I | 14 |  | 75 |  | FALSE |  | Seal Natural Stone | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Fireplace Stone | 1 |  |  |  | 1
1 | 3700 | K | 14 |  | 80 | 77 | FALSE |  | Hallmark measure | Hallmark Doors Ltd. |  | FALSE | FALSE | FALSE |  | 320 | Finishing Carpenter 1st | 1 |  |  |  | 1
1 | 3702 | I | 14 |  |  |  | FALSE |  | Pickup Leftover Finishing Material | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Finishing Carpenter 1st | 1 |  |  |  | 1
1 | 3720 | I | 14 |  | 90 |  | TRUE | 100 | Drywall Repairs and Light Check | Lessard Drywall |  | FALSE | FALSE | FALSE |  | 854 | Finishing Carpenter 1st | 1 |  |  |  | 2
1 | 3722 | I | 14 |  | 95 |  | TRUE | 105 | Sweep for Painters | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Drywall Repairs and Light Check | 1 |  |  |  | 1 | [6 empty] | PM
1 | 3745 | I | 14 |  | 100 |  | TRUE | 107 | On Site Lacquer | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Drywall Repairs and Light Check | 2 |  |  |  | 1
1 | 3747 | I | 14 |  | 105 |  | FALSE |  | Protect Woodwork | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | On Site Lacquer | 1 |  |  |  | 1 | [6 empty] | AM
1 | 3750 | I | 14 |  | 110 |  | TRUE | 110 | Painters 2nd Coat | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 180 | On Site Lacquer | 1 | 580 |  |  | 4
1 | 3767 | I | 14 |  |  |  | FALSE |  | Deliver Shelves | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Painters 2nd Coat | 1 |  |  |  | 1
1 | 3780 | I | 14 |  | 120 |  | TRUE | 120 | Laminate counters Installation | Classic Woodcrafting |  | FALSE | FALSE | FALSE |  | 120 | Painters 2nd Coat | 0 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3790 | I | 14 |  | 130 |  | TRUE | 130 | Granite counter install | Allstone Inc. |  | FALSE | FALSE | FALSE |  | 125 | Painters 2nd Coat | 0 |  |  |  | 1
1 | 3818 | K | 14 |  | 140 |  | FALSE |  | Ship ceiling fixtures to electrician | Park Lighting |  | FALSE | FALSE | FALSE |  | 220 | Painters 2nd Coat | -1 |  |  |  | 1
1 | 3825 | K | 14 |  | 160 |  | FALSE |  | K-Jay Ceiling Fixtures (no plates) | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Painters 2nd Coat | 1 |  |  |  | 1
1 | 3830 | K | 14 |  | 170 |  | TRUE | 5 | Closet and Cabinet Shelving | Guudenteit Finishing Carpentry |  | FALSE | FALSE | FALSE |  | 1325 | Painters 2nd Coat | 1 |  |  |  | 2
1 | 3835 | K | 14 |  | 180 |  | TRUE | 10 | Hartwell install | Hartwell Glass |  | FALSE | FALSE | FALSE |  | 340 | Closet and cabinet shelving | 0 |  |  |  | 1 | [6 empty] | AM please
1 | 3855 | K | 14 |  | 190 |  | TRUE | 15 | Security Completion | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 500 | Closet and cabinet shelving | 0 |  |  |  | 1
1 | 3860 | K | 14 |  | 200 |  | FALSE |  | Sound system completion | Integrated Home Systems |  | FALSE | FALSE | FALSE |  | 505 | Closet and cabinet shelving | 0 |  |  |  | 1
1 | 3890 | J | 14 |  |  |  | TRUE | 10 | Sweep House for Tile | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Closet and cabinet shelving | 1 |  |  |  | 1 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3900 | J | 14 |  | 210 |  | FALSE |  | Site Finish Hardwood (1st Coat) | 152229 Alberta Inc. |  | FALSE | FALSE | FALSE |  | 860
1 | 3910 | J | 14 |  | 220 |  | TRUE | 20 | Ceramic tile install | The Tile Company |  | FALSE | FALSE | FALSE |  | 140 | Sweep House for Tile | 1 |  | 750 | 6756 | -1 | [6 empty] | Remember to talk to setter about 45deg tub`s. Mitre tile`s..no grout…caulk.
1 | 3920 | K | 14 |  | 230 |  | FALSE |  | Shower doors measure | Top Shelf Closets & Glass Inc. |  | FALSE | FALSE | FALSE |  |  | Ceramic tile install | 1 |  |  |  | 1
1 | 3930 | K | 14 |  | 240 |  | FALSE |  | Shower Doors-Install | Top Shelf Closets & Glass Inc. |  | FALSE | FALSE | FALSE |  | 640 | Shower doors measure | 5 |  |  |  | 1 | [6 empty] | Allow three weeks for 10mm glass
1 | 3935 | J | 14 |  | 245 |  | FALSE |  | Lino Install | OMT Flooring |  | FALSE | FALSE | FALSE |  | 610 | Ceramic tile install | 0 |  |  |  | 1
1 | 3940 | J | 14 |  | 250 |  | TRUE | 30 | Northgate 1st | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Ceramic tile install | 1 |  |  |  | 1 | [6 empty] | Move to before hardwood if kitchen hardwood exists. | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3960 | J | 14 |  | 260 |  | TRUE | 40 | Hardwood Floors (Prefinished)-Install | 152229 Alberta Inc. |  | FALSE | FALSE | FALSE |  | 860 | Ceramic tile install | 2 |  | 900 | 6751 | -1
1 | 3970 | J | 14 |  | 270 |  | FALSE |  | Laminate floor install | 152229 Alberta Inc. |  | FALSE | FALSE | FALSE |  | 860
1 | 3980 | J | 14 |  |  |  | FALSE |  | Vac House for Carpet 1st | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Hardwood Floors (Prefinished)-Install | 1 |  |  |  | 1
1 | 3990 | J | 14 |  | 290 |  | TRUE | 55 | Carpet Install | OMT Flooring |  | FALSE | FALSE | FALSE |  | 610 | Vac House for Carpet 1st | 1 |  | 1000 | 6740 | [8 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 3995 | J | 14 |  |  |  | FALSE |  | Vac House for Carpet 2nd | Salvi Homes |  | TRUE | FALSE | FALSE
1 | 4020 | K | 14 |  | 310 |  | FALSE |  | Substantial Comp. Certificate | Tara Peters |  | FALSE | FALSE | FALSE |  |  | Carpet Install | 0 |  |  |  | 1
1 | 4030 | K | 14 |  | 320 | 77 | FALSE |  | Hallmark install | Hallmark Doors Ltd. |  | FALSE | FALSE | FALSE |  | 320 | Carpet Install | 1 |  |  |  | 1
1 | 4060 | K | 14 |  | 330 |  | TRUE |  | 2nd Finishing Package | Igloo Building Supplies |  | FALSE | FALSE | FALSE |  | 480 | Carpet Install | 1 |  |  |  | 1
1 | 4065 | K | 14 |  | 340 |  | TRUE | 30 | Finish Carpenter 2nd | Millenium Woodwork Ltd |  | FALSE | FALSE | FALSE |  | 580 | 2nd Finishing Package | 0 |  |  |  | 1
1 | 4066 | K | 14 |  | 350 |  | TRUE | 40 | Cabinet doors and accessory install | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Finish Carpenter 2nd | 1 |  |  |  | 1
1 | 4067 | K | 14 |  | 360 |  | FALSE |  | Dishwasher Delivery | Trail Appliances |  | FALSE | FALSE | FALSE |  | 870 | Finish Carpenter 2nd | 1 |  |  |  | 1 | [6 empty] | To Jobsite | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 4068 | K | 14 |  | 365 |  | FALSE |  | OTR Microwave Delivery | Trail Appliances |  | FALSE | FALSE | FALSE |  | 870 | Finish Carpenter 2nd | 1 |  |  |  | 1 | [6 empty] | To salvi shop
1 | 4069 | K | 14 |  | 380 |  | TRUE | 20 | Plumbing 2nd | Northgate Plumbing |  | FALSE | FALSE | FALSE |  | 600 | Dishwasher Delivery | 1 |  |  |  | 1
1 | 4072 | K | 14 |  | 390 |  | FALSE |  | Vac Completion | Readco Industries |  | FALSE | FALSE | FALSE |  | 630 | Finish Carpenter 2nd | 1 |  |  |  | 1 | [6 empty] | Only for complete system
1 | 4073 | K | 14 |  | 400 |  | FALSE |  | Heating Final | Accent Heating |  | FALSE | FALSE | FALSE |  | 30 | Northgate 2nd | 0 |  |  |  | 1 | [6 empty] | FIRST AM. Remove temp furnace at this time-plumber will be there to hook up. Power will be ready to go. ??? Registers in hardwood.
1 | 4074 | K | 14 |  | 410 |  | FALSE |  | Gemco Fireplace Lock-out | Gemco Fireplace |  | FALSE | FALSE | FALSE |  | 300 | Finish Carpenter 2nd | 1 |  |  |  | 1
1 | 4075 | K | 14 |  |  |  | FALSE |  | Final Cleaning of House | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Finish Carpenter 2nd | 1 |  |  |  | 1
1 | 4088 | K | 14 |  | 435 |  | FALSE |  | Built in appliance delivery | Trail Appliances |  | FALSE | FALSE | FALSE |  | 870 | Final Cleaning of House | 0 |  |  |  | 1 | [6 empty] | To salvi shop
1 | 4090 | K | 14 |  | 440 |  | TRUE | 60 | Install built in appliances | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Final Cleaning of House | 1 |  |  |  | 0 | [6 empty] | Move to before hardwood for OMW-ovens etc. | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 4145 | K | 14 |  | 460 |  | FALSE |  | Ship Remainder Fixtures | Park Lighting |  | FALSE | FALSE | FALSE |  | 220 | Final Cleaning of House | 2 |  |  |  | 1
1 | 4150 | K | 14 |  | 470 | 6 | TRUE | 70 | Painters 3rd Coat | Wild Rose Country Painting and Decorating Ltd. |  | FALSE | FALSE | FALSE |  | 182 | Final Cleaning of House | 2 | 900 |  |  | 2 | [7 empty] | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 4154 | K | 14 |  | 450 |  | FALSE |  | Window Lock-Out | Gienow Window & Door |  | FALSE | FALSE | FALSE |  | 310 | [12 empty] | Wednesdays only
1 | 4155 | K | 14 |  | 480 |  | TRUE | 90 | K-Jay Final | KJ Electric |  | FALSE | FALSE | FALSE |  | 520 | Painters 3rd Coat | 1 |  |  |  | 1 | [6 empty] | Must be done on this day! House being cleaned the following day and access will not be granted.
1 | 4190 | J | 14 |  | 490 |  | FALSE |  | Site Finish Hardwood (Final Coat) | 152229 Alberta Inc. |  | TRUE | FALSE | FALSE |  | 860
1 | 4220 | K | 14 |  | 510 |  | FALSE |  | New Home Warranty Inspection | Alberta New Home Warranty | Aubrey Funk | TRUE | FALSE | FALSE
1 | 4225 | K | 14 |  | 520 |  | FALSE |  | Confirm garage turnover (if required) | Aubrey Funk |  | TRUE | FALSE | FALSE
1 | 4280 | K | 14 |  | 530 |  | FALSE |  | Free Standing Appliance Delivery | Trail Appliances |  | TRUE | FALSE | FALSE |  | 870
1 | 4290 | K | 14 |  | 535 |  | TRUE | 95 | Pro Cleaning 1st Stage | Mona Blair |  | FALSE | FALSE | FALSE |  | 188 | K-Jay Final | 1 |  |  |  | 1
1 | 4299 | K | 14 |  | 540 |  | TRUE | 100 | Prep for Pre-Occ | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Pro Cleaning 1st Stage | 1 | 550 |  |  | 4
1 | 4300 | K | 14 |  | 538 |  | FALSE |  | Range Delivery (Gas or Electric) | Trail Appliances |  | FALSE | FALSE | FALSE |  | 870 | Prep for Pre-Occ | -1 |  |  |  | 1 | [6 empty] | To Jobsite
1 | 4331 | K | 14 |  | 577 |  | FALSE |  | Garage and Outside Clean Up | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Prep for Pre-Occ | -1 |  |  |  | 1
1 | 4332 | K | 14 |  | 500 |  | TRUE | 80 | Occupancy Inspection /Certificate | Strathcona County |  | FALSE | FALSE | FALSE |  |  | Prep for Pre-Occ | -1 |  |  |  | 1
1 | 4333 | K | 14 |  | 550 |  | FALSE |  | Wall-Paper |  |  | TRUE | FALSE | FALSE
1 | 4334 | K | 14 |  | 560 |  | FALSE |  | Specialty Painting | Wild Rose Country Painting and Decorating Ltd. |  | TRUE | FALSE | FALSE |  | 180
1 | 4335 | K | 14 |  | 570 |  | TRUE | 110 | Pro Cleaning 2nd Stage | Mona Blair |  | FALSE | FALSE | FALSE |  | 188 | Prep for Pre-Occ | 1 |  |  |  | 1 | [6 empty] | AM please | IIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIIII
1 | 4338 | K | 14 |  | 575 |  | FALSE |  | Photographer on site | Curtis Comeau Photography |  | FALSE | FALSE | FALSE |  | 735 | Prep for Pre-Occ | 1 |  |  |  | 1 | [6 empty] | Afternoon please
1 | 4350 | K | 14 |  | 580 |  | TRUE | 120 | Pre-Occupancy Inspection | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Pro Cleaning 2nd Stage | 1 |  |  |  | 1
1 | 4370 | M |  |  |  |  | FALSE |  | Forward RPR to Spratlin | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4380 | M |  |  |  |  | FALSE |  | Prepare statement of adjustments | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4390 | M |  |  |  |  | FALSE |  | Prepare final closing letter & documents | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4400 | M |  |  |  |  | FALSE |  | Prepare seasonal deficency list | Aubrey Funk | George Salvalaggio | FALSE | FALSE | FALSE
1 | 4410 | M |  |  |  |  | FALSE |  | Prepare turnover package | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4420 | M |  |  |  |  | FALSE |  | Prepare pre-occ list for turnover | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4430 | M |  |  |  |  | FALSE |  | Certificate of possesion signed | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4440 | M |  |  |  |  | FALSE |  | Prepare letter to release seasonal deficency | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4450 | M |  |  |  |  | FALSE |  | Confirm funds are in place for possesion | Tara Peters |  | FALSE | FALSE | FALSE
1 | 4470 | K | 14 |  | 620 |  | FALSE |  | Prep for Turnover | Salvi Homes |  | FALSE | FALSE | FALSE |  |  | Pre-Occupancy Inspection | 1 | 1000 |  |  | 3
1 | 4471 | K | 14 |  | 590 |  | FALSE |  | Furniture | Salvi Homes |  | TRUE | FALSE | FALSE |  |  | Prep for Turnover | 1 |  |  |  | 2
1 | 4472 | K | 14 |  | 600 |  | FALSE |  | Drapes |  |  | TRUE | FALSE | FALSE |  |  | Prep for Turnover | 2 |  |  |  | 1
1 | 4474 | K | 14 |  | 630 |  | FALSE |  | Telephones--Show Homes | Telus Communictions |  | TRUE | FALSE | FALSE |  |  | Photographer on site | 0 |  |  |  | 1
1 | 4475 | K | 14 |  | 640 |  | FALSE |  | Security ShutDown/StartUp (ShowHomes) |  |  | TRUE | FALSE | FALSE |  |  | Telephones--Show Homes | 1 |  |  |  | 1
1 | 4480 | K | 14 |  | 650 |  | TRUE | 130 | Turnover | Salvi Homes | Aubrey Funk | FALSE | FALSE | FALSE |  |  | Prep for Turnover | 1 |  |  |  | 1